## Sheet1
# | Description | Status/Progress | Closure Date
1 | Preparation Status/Update of questionnaires for ww14 customer survey.
2 | EGS MV ppt proposal plan with new timeline for mid July – Inventec need to communicate to their mgmt. to get machine time. | WIP - Jesse to complete by end of ww15 | target ww15.5
3 | FTT IDF/patent status and new video (include the top side of the tool) | IDF review complete. Decision was not to file for patent - can now share with customers updated video shared and resolution reduced to compress file size | ww15
4 | BHR socket samples for Quanta | Alex H to provide 5 sockets and 5 YTBs to ship to Quanta. Need shipping info to share with Alex for shipment and location to share with Larry P for equip supplier comms | target ww15.5
5 | CPTD BHR DOE with Fuji status | DOE completed. Fuji will share data directly with Quanta. Need Quanta location and Fuji will reach out to Quanta | completed ww14
6 | Package weight, ICX/CPX PMD into MAS or include in package attributes table | Added to draft of MAS | ww14
7 | Define sunset criteria for LFF Enabling WG |  | target ww16.4
8 | Revisit LFF Enabling WG mtg frequency and time slot | changed to 2x/month. Looking for another time slot if possible